## LEAD
PROJECT NAME - Complaint Redressal System GROUP NUMBER - 02 TEAM LEAD & FRONTEND LEAD - Cherala Ramani BACKEND LEAD - Jambugari Surendranath

## STATUS TRACK
Project Status Check
Date | EMP ID | Name | Domain (Frontend /Backend /Database Part
2022-05-05 | 2499841 | Aditya Kumar Saurabh | Discussion about Project
2022-05-05 | 2500947 | Ramineni Divya | Discussion about Project
2022-05-05 | 2496200 | Sinchana PD | Discussion about Project
2022-05-05 | 2500712 | K Pujith reddy | Discussion about Project
2022-05-05 | 2499858 | Muthyala Sushmitha | Discussion about Project
2022-05-05 | 2498852 | Cherala ramani | Discussion about Project
2022-05-05 | 2498035 | Vutkuri chikitha | Discussion about Project
2022-05-05 | 2498384 | Udayagiri Vamshi Krishna | Discussion about Project
2022-05-05 | 2500149 | Jambugari S | Discussion about Project
2022-05-05 | 2498308 | Mansi Mate | Discussion about Project
2022-05-06 | 2499841 | Aditya Kumar Saurabh | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2500947 | Ramineni Divya | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2496200 | Sinchana PD | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2500712 | K Pujith reddy | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2499858 | Muthyala Sushmitha | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2498852 | Cherala ramani | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2498035 | Vutkuri Chikitha | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2498384 | Udayagiri Vamshi Krishna | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2500149 | Jambugari S | Flow Chart Discussion and Data Base Schema
2022-05-06 | 2498308 | Mansi Mate | Flow Chart Discussion and Data Base Schema
2022-05-07 | 2499841 | Aditya Kumar Saurabh | Started working on frontend Part
2022-05-07 | 2500947 | Ramineni Divya | Started working on frontend Part
2022-05-07 | 2496200 | Sinchana PD | Started working on frontend Part
2022-05-07 | 2500712 | K Pujith reddy | Started working on Backend Part
2022-05-07 | 2498308 | Mansi Mate | Started working on frontend Part
2022-05-07 | 2498852 | Cherala ramani | Started working on Backend Part
2022-05-07 | 2498035 | Vutkuri Chikitha | Started working on Backend Part
2022-05-07 | 2498384 | Udayagiri Vamshi Krishna | Started working on Backend Part
2022-05-07 | 2500149 | Jambugari S | Started working on Backend Part
2022-05-07 | 2499858 | Muthyala Sushmitha | Started working on Backend Part
2022-05-09 | 2499841 | Aditya Kumar Saurabh | Working on Admin Module
2022-05-09 | 2500947 | Ramineni Divya | Working on Admin Module
2022-05-09 | 2496200 | Sinchana PD | Working on Customer Module
2022-05-09 | 2500712 | K Pujith reddy | Working on customer module
2022-05-09 | 2499858 | Muthyala Sushmitha | Working on Complaint module
2022-05-09 | 2498852 | Cherala ramani | Working on Complaint module
2022-05-09 | 2498035 | Vutkuri Chikitha | Working on Engineer Module
2022-05-09 | 2498384 | Udayagiri Vamshi Krishna | Working on Engineer Module
2022-05-09 | 2500149 | Jambugari S | Working on feedback Module
2022-05-09 | 2498308 | Mansi Mate | Working on feedback Module
2022-05-10 | 2499841 | Aditya Kumar Saurabh | Working On Junit
2022-05-10 | 2500947 | Ramineni Divya | Working On Junit
2022-05-10 | 2496200 | Sinchana PD | Working On Junit
2022-05-10 | 2500712 | K Pujith reddy | Working On Junit
2022-05-10 | 2499858 | Muthyala Sushmitha | Working on Frontend Error
2022-05-10 | 2498852 | Cherala ramani | Working on Backend Error
2022-05-10 | 2498035 | Vutkuri Chikitha | Working on Backend Error
2022-05-10 | 2498384 | Udayagiri Vamshi Krishna | Working on Integration Part
2022-05-10 | 2500149 | Jambugari S | Working on Integration Part
2022-05-10 | 2498308 | Mansi Mate | Working on Integration Part
2022-05-11 | 2499841 | Aditya Kumar Saurabh | Completed Junit
2022-05-11 | 2500947 | Ramineni Divya | Completed Junit
2022-05-11 | 2496200 | Sinchana PD | Completed Junit
2022-05-11 | 2500712 | K Pujith reddy | Completed Junit
2022-05-11 | 2499858 | Muthyala Sushmitha | Completed PPt and Documentation
2022-05-11 | 2498852 | Cherala ramani | Completed PPt and Documentation
2022-05-11 | 2498035 | Vutkuri Chikitha | Completed PPt and Documentation
2022-05-11 | 2498384 | Udayagiri Vamshi Krishna | Completed Integration Part
2022-05-11 | 2500149 | Jambugari S | Completed Integration Part
2022-05-11 | 2498308 | Mansi Mate | Completed Integration Part

## STATUS MEETING
Status Meeting Group - 02 (VB Batch)
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collabration
2022-05-05 | 10:30 | Checked | 14:00 | Checked | 17:00 | Checked
2022-05-06 | 10:30 | Checked | 13:30 | Checked | 17:30 | Checked
2022-05-07 | 10:30 | Checked | 14:00 | Checked | 17:30 | Checked
2022-05-08 | 10:30 | Checked | 13:00 | Checked | 18:45 | Checked
2022-05-09 | 10:30 | Checked | 14:00 | Checked | 18:00 | Checked
2022-05-10 | 10:30 | Checked | 14:00 | Checked | 17:00 | Checked
2022-05-11 | 10:30 | Checked | 13:30 | Checked | 17:00 | Checked